## Gantt Chart
GROUP 3 BLACKJACK GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Black Jack Project |  |  |  |  | COMPANY NAME | [6 empty] | Group 5
PROJECT MANAGER |  | Professor Christopher Smith |  |  |  |  | DATE | [6 empty] | 2024-10-02
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE |  |  |  |  | PHASE TWO | [19 empty] | Phase 3
[7 empty] | End Phase One |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Requirements Phase
1.1 | Research BlackJack Rules | Everyone | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2 | SRS | Everyone | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.1 | SRS- Class Diagrams | Oscar | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.2 | SRS - Sequence Diagrams | Oscar | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.3 | SRS - Use Case Diagrams | Carolina | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.4 | SRS - Use cases | Carolina | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.5 | SRS - Common Requirements | Santiago | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.6 | SRS - Nonfunctional Requirements | Santiago | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.3 | Powerpoint | Nikolas | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.4 | Gantt Chart | Santiago | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
2 | Design Phase (10/08/24 to 10/30/24)
| Draft Document | Everyone | bar: WEEK 1 W to WEEK 2 M
2.1 | Design Document | Everyone | 2024-10-09 | 2024-10-24 | 15 | 100% | bar: WEEK 2 T to WEEK 3 W
2.2 | UML Diagram | Everyone | 2024-10-10 | 2024-10-25 | 15 | 100% | bar: WEEK 2 T to WEEK 3 T
2.3 | Interface Design | Everyone | 2024-10-11 | 2024-10-26 | 15 | 100% | bar: WEEK 2 T to WEEK 2 R
2.4 | Client Server Architecture and Multithreading | Everyone | 2024-10-10 | 2024-10-14 | 4 | 100% | bar: WEEK 2 R to WEEK 3 M
2.6 | Design Card class, account class, user class | Carolina | 2024-10-12 | 2024-10-23 | 11 | 100% | bar: WEEK 1 F to WEEK 2 F
2.7 | Design Deck Class, show class | Carolina | 2024-10-13 | 2024-10-23 | 10 | 100% | bar: WEEK 1 F to WEEK 3 M
2.9 | Design Lobby Class | Everyone | 2024-10-15 | 2024-10-24 | 9 | 100%
3 | Design Table Class | Everyone | 2024-10-15 | 2024-10-25 | 10 | 100%
3.1 | Use cases - Update from SRS | Carolina | 2024-10-17 | 2024-10-23 | 6 | 100% | bar: WEEK 2 F to WEEK 3 T
3.2 | New Use cases | Brandom | 2024-10-18 | 2024-10-23 | 5 | 100% | bar: WEEK 3 W to WEEK 4 M
3.3 | Sequence Diagrams | Matthew | 2024-10-19 | 2024-10-28 | 9 | 85% | bar: WEEK 4 M to WEEK 4 R
3.4 | Github Update | Santiago, Carolina | 2024-10-19 | 2024-10-31 | 12 | 100% | bar: WEEK 4 M to WEEK 4 R
3.5 | Slides | Nikolas | 2024-10-29 | 2024-10-31 | 2 | 100% | bar: WEEK 4 M to WEEK 4 R
3 | Implementation Phase
3 | Implementation |  | 2024-11-01 | 2024-12-05 | 34 | 0% | bar: WEEK 6 M to WEEK 6 F
3.1 | Structure folder in github |  | 2024-11-01 | 2024-11-05 | 4 | 0% | bar: WEEK 5 T to WEEK 5 W
3.2 | Implement Server Class |  | 2024-11-01 | 2024-11-20 | 19 | 0% | bar: WEEK 7 T to WEEK 8 T
3.3 | Implement Client Class |  | 2024-11-01 | 2024-11-20 | 19 | 0% | bar: WEEK 7 T to WEEK 8 T
3.4 | Github Practice |  | 2024-11-01 | 2024-11-20 | 19 | 0% | bar: WEEK 5 W to WEEK 5 F
3.5 | Implement Cards, Deck, shoe class nad testing |  | 2024-11-01 | 2024-11-13 | 12 | 0% | bar: WEEK 5 F to WEEK 6 W
3.6 | Implement Account ,Class - testing |  | 2024-11-01 | 2024-11-13 | 12 | 0% | bar: WEEK 6 M to WEEK 7 T
3.7 | Implement User Class - testing |  | 2024-11-01 | 2024-11-13 | 12 | 0% | bar: WEEK 6 M to WEEK 7 T
3.8 | Implement Lobby Class - testing |  | 2024-11-01 | 2024-11-13 | 12 | 0% | bar: WEEK 6 M to WEEK 7 T
3.9 | Implement Table Class - testing |  | 2024-11-01 | 2024-11-13 | 12 | 0% | bar: WEEK 6 M to WEEK 7 T
4 | GUI / |  | 2024-11-25 | 2024-12-05 | 10 | 0% | bar: WEEK 8 M to WEEK 9 T
4.2 | Merge / Testing (server/client/gui) |  | 2024-11-25 | 2024-12-05 | 10 | 0% | bar: WEEK 8 M to WEEK 9 W
4.3 | Demo/ presentation |  | 2024-11-25 | 2024-12-05 | 10 | 0% | bar: WEEK 9 T to WEEK 9 F
4.4 |  |  |  |  | 0 | 0%