## Gantt Chart
GROUP 3 BLACKJACK GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Black Jack Project |  |  |  |  | COMPANY NAME | [6 empty] | Group 3
PROJECT MANAGER |  | Professor Christopher Smith |  |  |  |  | DATE | [6 empty] | 2024-10-02
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE |  |  |  |  | PHASE TWO | [19 empty] | PHASE THREE | [24 empty] | PHASE FOUR
[7 empty] | End Phase One |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Requirements Phase
1.1 | Research BlackJack Rules | Everyone | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2 | SRS | Everyone | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.1 | SRS- Class Diagrams | Oscar | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.2 | SRS - Sequence Diagrams | Oscar | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.3 | SRS - Use Case Diagrams | Carolina | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.4 | SRS - Use cases | Carolina | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.5 | SRS - Common Requirements | Santiago | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.2.6 | SRS - Nonfunctional Requirements | Santiago | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.3 | Powerpoint | Nikolas | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
1.4 | Gantt Chart | Santiago | 2024-09-05 | 2024-10-03 | 28 | 100% | bar: End Phase One M to End Phase One R
2 | Design Phase
2 | Design | Everyone | 2024-10-08 | 2024-10-31 | 23 | 0% | bar: WEEK 1 T to WEEK 4 R
2.1 | Design Server Class |  | 2024-10-08 | 2024-10-14 | 6 | 0% | bar: WEEK 1 T to WEEK 2 M
2.2 | Design Client Class |  | 2024-10-08 | 2024-10-14 | 6 | 0% | bar: WEEK 1 T to WEEK 2 M
2.3 | Desing Account Class |  | 2024-10-15 | 2024-10-18 | 3 | 0% | bar: WEEK 2 T to WEEK 2 F
2.4 | Desing User Class |  | 2024-10-18 | 2024-10-23 | 5 | 0% | bar: WEEK 2 F to WEEK 3 W
2.5 | Design Lobby Class |  | 2024-10-23 | 2024-10-28 | 5 | 0% | bar: WEEK 3 W to WEEK 4 M
2.6 | Design Table Class |  | 2024-10-28 | 2024-10-31 | 3 | 0% | bar: WEEK 4 M to WEEK 4 R
3 | Implementation Phase
3 | Implementation |  | 2024-11-05 | 2024-12-05 | 30 | 0% | bar: WEEK 5 T to WEEK 8 R
3.1 | Implement Server Class |  | 2024-11-05 | 2024-11-11 | 6 | 0% | bar: WEEK 5 T to WEEK 6 M
3.2 | Implement Client Class |  | 2024-11-05 | 2024-11-11 | 6 | 0% | bar: WEEK 5 T to WEEK 6 M
3.3 | Implement Account Class |  | 2024-11-12 | 2024-11-15 | 3 | 0% | bar: WEEK 6 T to WEEK 6 F
3.4 | Implement User Class |  | 2024-11-15 | 2024-11-20 | 5 | 0% | bar: WEEK 6 F to WEEK 7 W
3.5 | Implement Lobby Class |  | 2024-11-20 | 2024-11-25 | 5 | 0% | bar: WEEK 7 W to WEEK 8 M
3.6 | Implement Table Class |  | 2024-11-25 | 2024-11-28 | 3 | 0% | bar: WEEK 8 M to WEEK 8 R
4 | Final Presentation
4 | Slides/Additional Material |  | 2024-11-25 | 2024-12-05 | 10 | 0% | bar: WEEK 8 M to WEEK 9 R
4.2 |  |  |  |  | 0 | 0%
4.3 |  |  |  |  | 0 | 0%
4.4 |  |  |  |  | 0 | 0%